## Slide 1: Unit 21 – P2 (21.2 – Task 2a)
Tasks involved in the organisation of events.

## Slide 2: 21.2 – Scenario (for P2, P3, P4, M1, D1)
You have just started working as an Events Organiser for an Events Management Company and have been asked to compile a folder (to be given to new staff) containing a range of documents and copies of PowerPoint presentations.
These documents will explain tasks involved in event planning as well as covering expectations of staff new to the events industry.
The company have a number of “live” events enquiries that they are working on and you have also been asked to compile two proposals for one event from the following options:

## Slide 3: Choose one of the following client briefs (see GOL/Teams for more details):
A client wishes to host a Christmas party for its 200 employees (who work in the banking sector).
A client wishes to host a leaver’s ball for 500 university students.
A client wishes to host an opening night for their new restaurant.
A client wishes to host a charity fashion show, to raise money for a children’s poverty charity.
A client wishes to host an awards ceremony to celebrate contribution to community sport in the Surrey area.
A client wishes to host a food festival the Guildford area.
A client wishes to host a multi-sports tournament for schools in the Surrey area.

## Slide 6: Use the “Party Planning” episode of The Apprentice to help make notes on your hand out:
http://estream.godalming.ac.uk/View.aspx?id=11357~5e~WDi0rIs2iJ
(from 6 minutes).

## Slide 7: 1. Taking client brief
What does the client want/need? (Objective? Time/Date? Budget? Size?).
This must remain the central focus of the whole event plan/execution.
Could be written or discussed (phone/face-to-face).
Anything unclear MUST be clarified.
Communication links MUST be established between client and organiser as soon as the brief is agreed.

## Slide 8: 2. Developing ideas and themes to meet the client needs
Needs must be clearly defined AND understood.
All ideas and themes should be discussed with the client before key decisions/bookings are made.
These must be realistic in terms of time/budget/resources available (including food/drink).
Theme should be linked to purpose and be compatible to guests/audience needs.

## Slide 9: 3. Researching potential event venue
Location?
Access?
Size?
Facilities?
Equipment?
Staff?
Flow of visitors?
Emergencies?
Availability?
Cost?
Décor/attractiveness?
Surrounding area?
How to book (and deadlines for booking).

## Slide 10: 4. Preparing the proposal(s).
It is common for the organiser to present a number of different proposals to the client, which meet the brief in different ways.
Once all the initial research is done, information is collated into an appropriate format to present to the client.
Each proposal should outline potential: Theme, venue, dates/times, how objectives will be met, estimated costs etc.
Each proposal should be researched in enough depth to be able to answer any questions the client has.
The organiser should be in a position to make recommendations and be flexible in meeting the client’s needs, to adapt/fine tune proposals.

## Slide 11: Once proposals have been presented to the client, they can make a decision to go ahead with the event (or not). With the basic outline of the event already decided, the finer details now need to be planned, and a timeline created for when planning tasks must be completed.

## Slide 12: 5. Deciding on venue appearance e.g. layout, decorations
Meeting the needs of the client?
Appropriate to objectives/guests/audience.
What has worked before?
Budget/timescale?
Sourcing specific items?
In keeping with the theme?
Health & Safety?

## Slide 13: 6. Sourcing materials, suppliers and contractors
Full list of resources/services needed.
Quotes?
Budget? Theme?
Availability?
Using partners/regular suppliers/contractors?
How to choose suppliers not previously used?
Timescales? Deadlines?
Technical requirements? (need for specialist staff).

## Slide 14: 7. Identifying and keeping within the budget
All Costs/overheads (Expenditure) must be identified and calculated.
Sources of income identified and calculated.
Dates of/deadlines for payments recorded.
Accuracy is essential – records should be kept, with all income/payments communicated to/agreed with the “treasurer” or finance staff.
Payment methods/dates must be agreed with the client, so that all costs can be covered when required.

## Slide 15: 8. Setting up marketing e.g. promotions, ticketing and sales
Budget? Timescale?
Methods/communications most appropriate to target market.
Theme.
AIDA.

## Slide 16: 9. Ensuring health and safety e.g. risk assessments, dealing with crowd control
Risk assessment.
Legal requirements.
Emergency procedures.
Staff training.

## Slide 17: 10. Establishing the tools to be used for evaluation and feedback
Will the client’s objectives/needs be met by your event?
How/when will we know this? (What tools can we use?)
Financial data.
Surveys/questionnaires.
Qualitative feedback (meeting with client).

## Slide 18: With all of these details planned/booked, the event should be ready to organise on the day it is scheduled for. All details should be checked again with the client before the event date. A schedule of tasks for the day of the event should also be drawn up and distributed to any staff managing the event on the day.